## Sheet1
Sr. No. | POA | Estimated Time | Responsible Person | Steps/Commands/Scripts
1 | Increase instances in Delhi region | 5 mins | Niranjan Vaity | UI based
2 | Remove Mumbai service from load balancer | 5 mins | Niranjan Vaity
3 | Now all traffic is diverted to the Delhi region | NA | Niranjan Vaity
4 | Add new database in Mumbai region and detach old database | 5 mins | Niranjan Vaity
5 | Add Mumbai service back to load balancer | 5 mins | Niranjan Vaity
6 | Now requests will be diverted to geographically nearest region, either Delhi or Mumbai. | NA | Niranjan Vaity
7 | Scale down additional instances in Delhi | 5 mins | Niranjan Vaity
8 | push utility will use new attached database from next day onwards. | NA
| Total time | 30 mins
Note: Old data will be moved to the different VM