## POA
Sr. No. | Tasks | Scripts | Date | Responsible Person | Est Time
1 | Prerequisites: route entries, df -h (space), cross checking of ip, password expiry check | Web server: df -h free -m top App Server: df -h free -m top ps -ef¦grep java ---Application DB server: ps -ef¦grep postgres df -h free -m top | 2023-02-24 | Paresh/Shakti/Bhakti | NA
2 | CTS raise for Taking clone | NA | 2023-02-24 | Paresh/Shakti/Bhakti | NA
3 | Before stopping take screenshot of application/Count of records in DB | NA | 2023-02-24 | Paresh/Shakti/Bhakti | 5 Mins
4 | CTS to stop web server, app server and database | httpd - k stop httpd -k start | 2023-02-24 | Paresh/Shakti/Bhakti | 5 Mins
5 | Wintel team to take clone | NA | 2023-02-24 | Clover_Wintel | 5 min
6 | Linux team will perform CIS hardening | NA | 2023-02-24 | Clover_Linux | 80 Mins
7 | Taking snapshot at VM level | NA | 2023-02-24 | Clover_Wintel | 5 Mins
8 | CTS to start databse, app server and web server | NA | 2023-02-24 | Paresh/Shakti/Bhakti | 5 Mins
9 | test the application - Testing Team | NA | 2023-02-24 | Paresh/Shakti/Bhakti/QA Team | 15 min

## Server List
VM Names | Physical IP | Natted IP | Project | Envirnment
Beckn-LR-Prod-APP2 | 10.130.18.83 | 172.21.23.83 | ONDC | Staging
Beckn-Pilot-Testing-APP1 | 10.130.18.80 | 172.21.23.80 | ONDC | Staging
Beckn-Pilot-Testing-APP2 | 172.30.151.104 | 172.30.151.104 | ONDC | Staging
Beckn-Pilot-Testing-DB2 | 172.30.151.107 | 172.30.151.107 | ONDC | Staging
Beckn-Pilot-Testing-WEB1 | 10.130.18.153 | 172.21.23.153 | ONDC | Staging