## Registry
Sr. No | Task | Steps | Command
1 | Downtime | 30 mins
2 | Deployment changes | Go to directory | /app/beckn/beckn_jars/registry/single-api/old_db/
|  | Verify directory contains beckn-np-onboarding-2.4.0.jar, config-buyer-preprod.json and application-preprod.yml | ls -lrth
|  | Take backup of existing jar | mv beckn-np-onboarding-2.4.0.jar beckn-np-onboarding/new-np-20092022
|  | compare and change application.yml file with 84 servers /app/beckn/beckn_jars/registry/single-api/old_db/application-test.properties | /app/beckn/beckn_jars/registry/single-api/old_db/application-test.properties
3 | DB Manual Entry | Add new entry of gateway for new domainONDC:RET10,ONDC:RET14 | ONDC:RET10,ONDC:RET14
4 | Sanity Testing Post Deployment | Test the functionality and deployed changes

## Gateway
Sr. No | Task | Steps | Command
1 | Downtime | 30 mins
1 | Take Backup and Copy | Go to directory | /app/beckn/beckn_jars/gateway/preprod/preprod-ins/ of 84 to /app/beckn/BG
|  | Verify directory contains | ls -lrth
|  | Take backup of existing jar with today's date | mv beckn-onsubscribe-demo-0.0.1.jar beckn-onsubscribe-demo-0.0.1.jar_03042023
|  | Property file changes | add this to property file of gateway max-history: 100 domains: nic2004:52110,nic2004:60232,ONDC:RET10,ONDC:RET14
|  | Verify files are backed up as | ls -lrth
2 | Database Changes | ALTER TABLE api_audit ADD COLUMN error_technical text; ALTER TABLE api_audit ADD COLUMN error_functional text; commit; sql script of table creation
3 | Sanity Testing Post Deployment | Test the functionality and deployed changes